PRODUCTION PLAN (BIO-SAND WATER FILTER)

RAPE HURTS FOUNDATION

ACTIVITY WORKPLAN-BSF CONSTRUCTION

| TIMING (WEEKS) | NUMBER OF YOUTH WORKING |  | ACTIVITIES (12 Moulds) | OUTPUT- AT THE END OF WEEK | ASSUMPTIONS |
| --- | --- | --- | --- | --- | --- |
| Week 1 10TH-16TH November | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 2 17th-23rd November | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 3 24th-30th November | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 4 1ST-7TH December | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 5 8-14th December | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 6 15th-21st December | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 7 27th-2ND December-January | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 8 3rd-9th January | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 9 10th-16th January | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 10 17th-23rd January | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 11 24TH-30TH January | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 12 31st-6th February | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 13 7th-13th February | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 14 14th-20th February | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 15 21st-27th February | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 16 28th-6th March | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 17 7th-13th March | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 18 14th-20th March | 29 Workers | 18 Youths | - Constructing BSFs | - 72 BSFs | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - 72 lids - 72 diffuser boxes |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Weekly report on the performance |  |
| Week 19 21st-27th March | 21 Workers | 10 Youths | - Constructing BSFs | - Finishing the remaining BSFs (4) - Replacing damaged filters | - The youths are all cooperative and physically capped - The weather is favourable - Time management is observed |
|  |  | 4 Youths | - Making lids and diffuser boxes | - Finishing the remaining the lids and diffusers (4) - Replacing damaged lids and diffusers |  |
|  |  | 6 Youths | - Sieving filtration Sand and Gravel | - 2400 kgs of filtration - 500 kgs of gravel |  |
|  |  | 1 Supervisor | - Monitoring and evaluation | - Project report on the BSF construction and assessment of workers |  |

Note: Workers will be working 6 days a week with the exclusion of working on Sunday and each will be paid per work done. Sunday maybe used for distributing the finished BSFs

Major  activities of a BSF construction

| Activities | Purpose | Materials | Time |
| --- | --- | --- | --- |
| Unbolting the mould to clean, oil it and insert the tube after which you bolt again | To prepare the mould for the new concrete to make a BSF | - Wire brush - Outlet tube - Cello tape - Cooking Oil - Cutter - Spanners - Tape measure | 1 hour |
| Sieving stone dust | To get small and large gravel which will be used in construction | - 12mm sieve - 6mm sieve - 0.7mm sieve - Spade | 25 minutes |
| Measuring and mixing the ingredients | To get exact amount required of gravel, sand and cement required and mix to make concrete | - A bucket with measurements - Water - Spade | 35 minutes |
| Using a trowel and a metal rod to settle the concrete down that has been put in the mould | To make sure all parts of the mould are filled with concrete without leaving spaces | - A metal rod - Trowel | 20 minutes |
| Banging all the sides of a mould from down up to the top consistently | To remove air bubbles from the concrete | - Rubber Mullet | 1hr |
| Removing the top layer | To remove the oily layer with the formed bubbles to make the bottom strong | - Trowel | 1 minute |
| Levelling the top |  | - Level - Trowel | 5 minutes |
| Waiting for the concrete to partially dry | To ensure the concrete has strengthened | - Timer | 45 minutes |
| Levelling and Making edges | To ensure that the bottom of the BSF is flat | - Level - Trowel - concrete | 10 minutes |
| Putting the Sand on top | To protect the BSF from direct from rain drops and people | - Sand - Spade | 1 minute |
| Remove the BSF by Unbolting (It’s done after 24hrs) | To expose the BSF to direct sun light to dry easily | - Timer - Spanners - Wood Blocks - Tire | 30 minutes |
| Cleaning the mould and storage | To prevent it from rusting when it’s not in use | - Wire brush | 10 minutes |
| Making Diffuser boxes and Lids | These two items are key components of the BSF | - Metallic Sheet - Scissors - Ruler - Tape measure - Rubber Mullet - A nail | 1 hour |